## On going Projects
Disclosure of Information on Development Projects for General Public as a Right of the People - 2023
On going Projects as at 01.01.2024 (Project which is awarded on or before 01.01.2024 and work started/ongoing)
Executing Agency |  | : State Ministry of Urban Development
Name of the Department/Institution/Project : |  |  | Siyak Nagara/ Urban Infrastructure and Township Development Programme
# | Name of the Project | Total Estimated Project Cost (Rs.Mn.) | Expected Duration of the Project | Location of the Project (Grama Niladhari Division /Divisional Secretariat Division /District Secretariat Division) | Financing Agency (GOSL/ Foreign) | Loan |  | Expected Benefits of the Project | Implementing Agency | Location of Project Management Unit | Project Components/ Activities | Contactor Details |  | Value of the Contract (Rs.Mn.)
[6 empty] | Amount (Rs.Mn.) | Interest Rate (%) |  |  |  |  | Name | Address
1. Siyak Nagara/ Urban Infrastructure & Township Development Programm
1 | Development of land acquired by the Urban Development Authority for administrative purpose at Gampola, Mahara - Stage II (new project) | 75 | 2023-09-01 2024-02-01 | Gampola DS | GOSL | - | - | Infrastructure Development for the proposed administration complex and mix development project | UDA | Project Management Division, UDA | Develop the part of main access road ,Drain and culwet development,Pedestrian path development | Central Engineering Services (Pvt) Ltd. (CESL) | No. 415, Bauddhaloka Mawatha, Colombo 07 | 24.9
2 | Nature corridor development along Nanu Oya stream at Nuwara Eliya | 120 | 5/1/2021 - 05/02/2023 | Nuwara Eliya DS |  | - | - | Landscape development |  | Environment & Landscape Division, UDA | Landscaping | M/S Malwatta | 119, Gampola Rd, Ulapane | 107.3
3 | Beach park Development at Nintavur Phase - I | 80 | 22/07/2021 17/04/2023 | Ampara DS |  | - | - | Sustained tourisum development samall scale economic development |  | Project Management Division, UDA | Beach park | Central Engineering Services (Pvt) Ltd. (CESL) | No. 415, Bauddhaloka Mawatha, Colombo 07 | 83.7
4 | Green Infrastructure Development along – “Vallaivelie” – Jogging Track Point Pedro | 70.2 | 9/1/2021 - 2/15/2023 | Jaffna DS |  | - | - | Promoting physical fitness and good health and increasing recreational facility among the people |  | Environment & Landscape Division, UDA | Walk way Track | NEMO Construction | Negombo Road,Paliyagoda | 70.17 original TEC. Require 5mn to complete this project to a usable quality
5 | Completion of bus stand at Mullativu (stage II) - (continuation) | 170 | 2023-05-06 2023-11-15 | Mullativu DS |  | - | - | Providing bus parking facilities |  | Project Management Division, UDA | Completion of 4,455 sq.ft. area bus stand (balance part of the existing bus stand) with 8 bus bays, 2 cafeterias, waiting areas and time keeper's room for both private and CTB | Sabach & Accociate | No. 602, Ahamad Rd, Sainamadu 16. | 70.44
6 | Redevelopment project of Rajapihilla Urban Park at Kurunegala (phase II) | 204.21 | 2021-08-21 2023-05-02 | Kurunegala DS |  | - | - | Providing recreational facilities |  | Environment & Landscape Division, UDA | Completion of urban park | Asiri Building Construction | 418, Udupila, Delgoda | 40.53
7 | Public fair development at Alawwa (stage II) | 50 | 2023-03-01 2024-09-01 | Kurunegala DS |  | - | - | Provide Facilities for Venders and Public |  | Project Management Division, UDA | 100% completion of existing 200m length access road widening and completion of balance landscaping and finishing work of weekly fair | Ashoka Construction | Henduwawa Kappetipola | 30.9
8 | Holuwagoda Agroecological Park phase I&II | 450.56 | 2021-08-05 2023-02-08 | Galle DS |  | - | - | Providing recreational facilities |  | Project Management Division, UDA | Completion of jogging track | SLLDC | 4 Sri Jayawardenepura Mawatha Welikada, Sri Jayawardenepura Kotte | 132
9 | Development of public market at Avissawella | 167.6 | 2021-08-02 2023-06-30 | Colombo DS |  | - | - | Providing market facilities for venders |  | Project Management Division, UDA | Completion of market | Daninton Construction | 854, Galle Rd, Katukurunda, Kaluthara. | 167
10 | Development of public market at Gampaha (stage II) | 420 | 9/25/2021-3/25/2023 | Gampaha DS |  | - | - | Development of public market |  | Project Management Division, UDA | Completion of market | Sripalie Construction(Pvt.) Ltd | No. 06, S.H. Dahanayake Mawatha, Kaluwella, Galle | 420
11 | Redevelopment of Oruthota walking path at Gampaha | 58.62 | 2021-06-26 2023-03-20 | Gampaha DS |  | - | - | City beatification |  | Environment & Landscape Division, UDA | Walk way Track | Sri Lanka Land Development Corporation | Welikada, Rajagiriya. | 54.2
12 | Department of Panadura market and multipurpose building | 539.2 | 2021-09-30 2023-12-31 | Kaluthara DS |  | - | - | Providing Building Facilities for venders |  | Project Management Division, UDA | Public market | Mode Enginering | 467, 1 Havelock Rd, Colombo 05 | 539.2

## New project
Disclosure of Information on Development Projects for General Public as a Right of the People - 2023
New Projects as at 01.01.2024 (Project which is approved (Cabinet/NPD) or submitted to Cabinet/NPD for approval or work to be started in 2023)
Executing Agency |  | : State Ministry of Urban Development
Name of the Department/Institution/Project : |  |  | Siyak Nagara/ Urban Infrastructure and Township Development Programme
# | Name of the Project | Total Estimated Project Cost (Rs.Mn.) | Expected Duration of the Project | Location of the Project (Grama Niladhari Division /Divisional Secretariat Division /District Secretariat Division) | Financing Agency (GOSL/ Foreign/ PPP) | Loan |  | Expected Benefits of the Project | Implementing Agency | Location of Project Management Unit | Project Components/ Activities | Approval Details |  | Present Status/ Stage of the Project
[6 empty] | Amount (Rs.Mn.) | Interest Rate (%) |  |  |  |  | Cabinet (Date & Number) | NPD (Date & Number)
1. Siyak Nagara/ Urban Infrastructure & Township Development Programm
1 | Malawawewa Landscaping project at Kekirawa - Stage II (New Project) | 24.95 | 2023-09-01 2024-02-01 | Kakirawa Ps | GoSL | - | - | Providing Refreshment and sanitory facilities | UDA | Project Management Division, UDA | Parking facilities,Restaurant and sanitory facilities gathering and waiting area |  | Concept paper was submitted.Approval is pending | Architectural Design/Preparation of Balnce BOQ were Completed
2 | Sanitary facilities development and landscaping at Habarana- -- Stage II (New Project) | 36.25 | 2023-09-01 2024-05-01 | Habarana PS |  | - | - | Providing sanitory facilities for Tourist /local and disable people |  | Project Management Division, UDA | sanitory facilities with Landscaped gathering area |  | Concept paper was submitted.Approval is pending | Architectural Design/Preparation of Balnce BOQ were Completed
3 | Proposed Pathway Construction of Ruwanweliseya Car Park to Jethawanarama Parallel Road at Anuradhapura Sacred City under the Sihilal Maga Pathway Development Project - Phase II | 58.3 | 2023-09-01 2024-05-24 | Anuradhapura PS |  | - | - | Provide facilities for Pilgrims and Visitors |  | Environment & Landscape Division, UDA | Provide facilities for Pilgrims and Visitors. Develop the Pedestrian Pathway Connecting two monastery areas using a pedestrian bridge. Provide the lighting facilities Shifting the existing temporary hall (365-day Dansala) to another place |  | SMUD/P&M4/PP/Vol 1 2021 UDA 01 (NCP) 2021 | The footpath was filled with soil in the first stage, and Architectural and Engineering drawings were completed. Preparation of BOQ is in progress.
4 | Proposed parking and pedestrian facilities improvement project at Alawwa (stage II) | 100 | 2023-03-01 2024-12-01 | Kurunegala DS |  | - | - | Construction of the 9m width pavement parallel to drain of Alawwa - Gorilla main street |  | Project Management Division, UDA | 100% completion of construction of 9m wide payments and 500m length |  | Submitted the proposal and recommendation from Ministry to DNP by letter number MUD&H/UDD/P&M-4/PP/2023 and dated 21.03,2021. DNP returned the documents due to lack of certain information. Resubmitted the details. | Architectural and Engineering drawings were completed. Preparation of BOQ is in progress
5 | Warakapola bus stand (stage II) | 280 | 2023-04-25 2024-04-24 | Warakapola Ps |  | - | - | Providing bus parking facilities |  | Project Management Division, UDA | City beatification |  | 2021/09/21 NPD/BA/2021 | Stage I Completed
6 | Diyandara Town Development Stage IV | 160 | 2023-12-02 2026-12-31 | Diyandara Ps |  | - | - | Landscape work |  | Project Management Division, UDA | City beatification |  |  | NPD Approval is in progress
7 | Boralesgamuwa multipurpose building (stage III) | 192 | 10/03/2023 24/12/2024 | Boralesgamuwa Ps |  | - | - | Construction of public facility building for the Urban Council |  | Project Management Division, UDA | Multi purpose building | NA | 2019.09.18 | Tender Document Submit to Ministry
8 | Peralanda wetland area recreational development project (stage III) | 154.5 | 2023-03-02 2023-11-30 | Gampaha DS |  | - | - | Providing recreational facilities |  | Environment & Landscape Division, UDA | Completion of park |  | Concept paper was submitted. | New Project. Not yet commence
9 | Public market Minuwangoda (stage III) | 30 | 2023-02-14 2023-12-14 | Gampaha DS |  | - | - | Providing market facilities for venders |  | Project Management Division, UDA | Completion of market | NA | 2018.09.04 | Tender Documents submit to Ministry
10 | Design & Construction of Proposed Horana Pola Stage IV- Balance Work | 20 | 2023-02-14 2023-12-16 | Horana DS |  | - | - | Completion of Service |  | Project Management Division, UDA | Completion of Transformer | NA | 2020.10.14 | Tender Document Submit to Ministry